## Sheet1
Project Name: Trace and GigIt
Author: Leela Krishna Kosaraju
Backend Testing
Feature Name | Summary | Execution Steps | Expected Results | Actual Result | Priority | Execution Status | Comments
Register Device API | When a user install application in a device, on app launch this API should be called so that a session will be created for the device | 1. On applaunch register API must be called. 2. If returning user on the same device, user will already be added to session else new session will be created. 3. Check whether data is available or inserted in the session table and device table. | 1. API should produce 200 response code. 2. In response, client key must be present. 3. There should valid records in tha database. 4. If returning user, client key must be updated and new key must not be generated. 5. when inserting in a session table, device must be attached to the session. | 1. Test case is failing if we change fields like profile,make and model | High | Failed | 1. We couldn't enter another device details. 2. Should check if the values are hard-coded or not
SignUp API | Input from Postman must be saved in Mysql | 1. To keep user name and password to be save in mysql through API 2. once the user is been registered same user details should not be accepted 3. if password conditions are not met user signup shouldn’t happen 4. to make sure that password is saved in encrypted format | 1. Response status code must be 200 2. Result type must be JSON | 1. Session ID missing. | High | Failed | It happened because register device API has failed.
Network Connection | Validate network IP address whether to allow request or not | 1. Switch on the server 2. Enter Server IP address in another device in the same network 3. Check whether the device is conneted to the server. | 1. Device is connected to the server 2. Http request must be timed out | 1. We connected to the server and got timed out | High | Success

## Sheet2
Project Name: Trace and GigIt
Author: Leela Krishna Kosaraju
Frontend Testing
Feature Name | Summary | Execution Steps | Expected Results | Actual Result | Priority | Execution Status | Comments
Install | Verify that the application is installed successfully. | 1. Installing through APK file 2. Open the application | The application should be installed successfully | The application is successfully installed on an android device | High | Success | Successfully Executed
Uninstall | Verify that the application is installed successfully. | 1. Go to settings on the device. 2. Select the application and click on Uninstall option. | The application should be Uninstalled successfully | The application is successfully Uninstalled from an android device | High | Success | Successfully Executed
Login | User/ Owner should be able to login in the application | 1. Check whether the User/Owner has proper internet connection 2. Check whether the username and password are correct. 3. Check whether the User/Owner is able to see the home page of the application | 1. User/Owner has proper internet connection 2. Username and password are correct. 3. User/Owner is redirected to homepage after they login |  | High | Pending
SignUp | New User/Owner should be able to signup or create their account | 1. Check whether the User/Owner has proper internet connection. 2. Check whether all the fields are properly filled or not. 3. User/Owner should be redirected to the respective homepage after SignUp | 1. User/Owner has proper internet connection 2. All the fields are filled properly in the signup page 3. User/Owner is redirected to homepage after they login |  | High | Pending
Animation Screen show URL | To show Url text entry box when long pressed on Logo of the animation screen | 1. Long press on the logo at the start of the app 2. Check whether URL text entry box is being displayed or not | 1. URL text entry box has to be displayed. 2. After entering the IP address, it should redirect to the login screen. | 1. After entering IP address, it is not redirecting to the login screen | Medium | Failed